## Sheet1
STANDARDS PROJECT | time axis 2020-01-01 to 2028-12-01
L1 LWR (Maioli) | 2020-01-01: Consensus Ballot; 2020-03-01: Respond to Ballot Comments; 2020-08-01: Recirculation Ballot; 2020-09-01: Respond to Ballot Comments; 2021-02-01: Re-Recirculation Ballot; 2021-03-01: Technical Editing; 2021-07-01: Ballot on Technical Editing; 2021-08-01: Re-Recirculation Ballot; 2021-09-01: BNCS Ballot; 2021-10-01: ANSI Public Comment Period; 2021-12-01: Editing (600 pages); 2022-04-01: SB Ballot; 2022-05-01: Publication as ANSI Standard; 2023-07-01: Consensus Ballot; 2023-08-01: Respond to comments; 2023-11-01: Recirculation Ballot; 2023-12-01: BNCS & SB Ballot + ANSI public comment period & Editing; 2024-03-01: Publication as ANSI Standard; 2024-05-01: Code Case Consensus Ballot; 2024-06-01: Respond to Comments on Code Case; 2025-05-02: Code Case Recirculation Ballot
LEVEL 2 PRA (Schneider) | 2020-01-01: Consensus Ballot; 2020-02-01: Respond to Ballot Comments; 2022-09-01: Recirculation Ballot; 2022-11-01: Address Recirculation Ballot Comments; 2023-04-01: Re-Recirculation Ballot; 2023-05-01: BNCS ballot; 2023-06-01: ANSI public comment period & Editing; 2023-08-01: Review Edits and Proofs; 2023-10-01: Delay for L1 Standard; 2024-02-01: Ballot to Confirm Editorial & Adopt 2024 L1 Standard; 2024-03-01: SB ballots; 2024-05-01: Publication as ANSI Standard
LEVEL 3 PRA (Teargarden) | 2020-01-01: Standard in Development; 2022-03-01: Ballot Read- iness Review; 2022-04-01: Address Readiness Review Comments; 2023-08-01: Consensus Ballot; 2023-09-01: Respond to comments Revise ballot material; 2024-07-01: Recirculation Ballot; 2024-08-01: BNCS ballot; 2024-09-01: ANSI public comment period & Editing; 2024-11-01: SB ballots; 2024-12-01: Review Edits and Proofs; 2025-01-01: Ballot to Confirm Editorial; 2025-02-01: Publication as ANSI Standard
LP/SD PRA (Sung) | 2020-01-01: Standard in Development; 2025-06-02: Ballot Readiness Review; 2025-10-02: Address Readiness Review Comments; 2026-01-02: Consensus Ballot; 2026-02-02: Respond to comments Revise ballot material; 2026-06-03: Recirculation Ballot; 2026-07-03: BNCS ballot; 2026-08-03: ANSI public comment period & Editing; 2026-10-03: SB ballots; 2026-11-03: Review Edits and Proofs; 2026-12-03: Ballot to Confirm Editorial; 2027-01-03: Publication as ANSI Standard
ALWR (incl SMR) (Bristol) | 2020-01-01: Standard in Development; 2025-10-02: Ballot Readiness Review; 2025-11-02: Address Readiness Review Comments; 2025-12-02: Consensus Ballot; 2026-01-02: Respond to comments Revise ballot material; 2026-05-03: Recirculation Ballot; 2026-06-03: BNCS ballot; 2026-07-03: ANSI public comment period & Editing; 2026-09-03: SB ballots; 2026-10-03: Review Edits and Proofs; 2026-11-03: Ballot to Confirm Editorial; 2026-12-03: Publication as ANSI Standard
Multi-Unit PRA (Summit) | 2020-01-01: Standard in Development; 2026-02-02: Ballot Read- iness Review; 2026-04-03: Address Readiness Review Comments; 2026-07-03: Consensus Ballot; 2026-08-03: Respond to comments Revise ballot material; 2026-12-03: Recirculation Ballot; 2027-01-03: BNCS ballot; 2027-02-03: ANSI public comment period & Editing; 2027-04-04: SB ballots; 2027-05-04: Review Edits and Proofs; 2027-06-04: Ballot to Confirm Editorial; 2027-07-04: Publication as ANSI Standard
NLWR PRA (Grabaskas) | 2020-01-01: Ballot Readiness Review; 2020-03-01: Address Readiness Review Comments; 2020-04-01: Consensus Ballot; 2020-06-01: Respond to Ballot Comment; 2020-08-01: Recirculation Ballot; 2020-09-01: BNCS Ballot; 2020-10-01: ANSI Public Comment Period & Editing; 2021-01-01: SB Ballot; 2021-02-01: Publication as ANSI Standard; 2021-03-01: Revise standard to achieve consistency with other standards, and to incorporate lessons learned.; 2023-04-01: Revise standard to achieve consistency with other standards, and to incorporate lessons learned.; 2026-09-03: Consensus Ballot; 2026-10-03: Respond to comments Revise ballot material; 2027-02-03: Recirculation Ballot; 2027-03-04: BNCS and SB ballots; 2027-04-04: ANSI public comment period; 2027-05-04: Editing (100 pages); 2027-07-04: Review Edits and Proofs; 2027-08-04: Ballot to Confirm Editorial; 2027-09-04: Publication as ANSI Standard
RG. 1.200 Rev. 4 (Humberstone) | 2026-12-03: Target for Technical Revision???
RG. 1.200 Rev. 5 (Humberstone) | 2028-12-01: Target for Technical Revision???
RG 1.247 (Humberstone) | 2022-01-01: PD Trial Use RG 1.247 Trial Use Period
IWG MEETINGS (Grantom)
JCNRM MEETINGS LOCATIONS (Martinez) | 2022-03-01: Feb 28-March 3 VIRTUAL; 2022-09-01: Sept 19-22 Chattanooga; 2023-02-01: Feb 27 - Mar 2 US Southwest; 2023-09-01: Sept 18-21 DC Area; 2024-02-01: Feb 26-29 EPRI; 2024-09-01: Sept. 16-19, 2024 Pittsburgh; 2025-02-01: Feb. 24-27, 2025 University of Maryland; 2025-09-02: ?????; 2026-02-02: ?????; 2026-09-03: ?????; 2027-02-03: ?????; 2027-09-04: ?????
BNCS MEETINGS LOCATIONS (Grantom)
ANS-SB MEETINGS LOCATIONS (Schroeder) | 2022-06-01: 14 Anaheim, CA; 2022-11-01: 15 Phoenix, AZ; 2023-06-01: June 13th; Indianapolis; 2023-11-01: November 14th, D.C.; 2024-06-01: June 1th; Las Vegas; 2024-11-01: November 19th, Orlando; 2025-06-02: June 17th; Chicago; 2025-11-02: November 11th, D.C.; 2026-06-03: June 2nd; Denver; 2026-11-03: November 17th, Phoenix; 2027-06-04: June 15th; Lake Buena Vista, FL; 2027-11-04: November 9th, D.C.
 | time axis 2022-01-01 to 2027-12-04